## OverView
Task Name | Duration | Start Date | Finish Date | Predecssor | Resource Name
IPAM Project Implementation | 86 Days
Project Kick-off and Planning Session | 0.5 Days | 2021-08-28 | 2021-08-28 |  | CitiusCloud
Basic BE Development | 5 Days | 2021-08-30 | 2021-09-03 | 3 | Raaj
BE with Sequelize | 5 Days | 2021-09-06 | 2021-09-10 | 4 | Raaj,Vikram
FE | 10 Days | 2021-09-13 | 2021-09-24 | 4 | Raaj,Vikram
Dockerize the IPAM | 5 Days | 2021-09-27 | 2021-10-01 | 6 | Raaj,Vikram
Sprint-1 | 5 Days | 2021-10-04 | 2021-10-08 | 6 | Raaj
Sprint-2 | 5 Days | 2021-10-11 | 2021-10-15 | 6 | Raaj,Vikram
Sprint-3 | 10 Days | 2021-10-18 | 2021-10-29 | 6 | Raaj,Vikram
Unit test and bug fixes | 20 Days | 2021-11-01 | 2021-11-26 | 10 | CC and Raaj
convert to Product(msi) and implement kubernetes | 10 Days | 2021-11-29 | 2021-12-10 | 11 | Vikram, Raaj
Final Validation | 5 Days | 2021-12-13 | 2021-12-17 | 12 | CC and Raaj
Documentation and Production Rollout | 5 Days | 2021-12-20 | 2021-12-24 | 13 | Raaj and CC
Project Closure | 0.5 Days | 2021-12-25 |  | 14 | CitiusCloud
Note: Public holidays and leaves were not counted in the plan. Parallel project were not accounted. Hence date creep expected.

## Infra Task Tracker
Task Name | Dependency | Resource Name | Complete(Yes/No) | Current Status
IPAM Project Implementation
Container Repository readiness
Kubernetes Repository Readiness
Laptop upgrade if required for 3 kubectl implementation

## Development Tracker
Task Name | Dependency | Resource Name | Complete(Yes/No) | Current Status
IPAM Project Implementation
Sprint-1 Tasks
Feature: Allow individual & compose Web UI login |  | Raaj
Fix: hide data in url |  | Raaj
Feature: Search as typed |  | Raaj
Feature: Field level validation |  | Raaj
Sprint-2 Tasks
Implement React Grid with sortable, editable, auto save, printable, searchable |  | Raaj
Sprint-3 Tasks
Adhere to Web UI project's UI | Web UI Project | Raaj
Implement msg/toast, error and log from Web UI Project | Web UI Project | Raaj

## Issue Tracker
Task Name | Dependency | Resource Name | Complete(Yes/No) | Current Status